## Start Here
G1 Bowling Training Plan
Eight weeks of tasks (Phases 0–4). Same content as docs/training_plan.md and the online page.
Start date (a Monday) | 46321 | Default from the plan (Mon 26 Oct 2026). Change it and every planned date updates.
How to use
Cells you edit | Yellow cells with blue text: the start date above, and Status, Date done, Hours and Notes on the Tasks sheet.
Status | Pick from the list: Not started, In progress, Done, Blocked. Done rows turn green, Blocked rows turn red.
Everything else | Formulas or plan text. Planned dates, the Progress sheet and the overall totals update by themselves.
Planned date | Weekday tasks: start date + 7 × (week − 1) + weekday. ML track tasks: that week's Sunday, the deliverable deadline.
Move on rule | Start the next week when the 'Done when' checks pass, not when the dates run out.
Example of a filled row
Status | Done
Date done | 2026-10-27
Hours | 1.5
Notes | Total robot mass 37.6 kg; README sizes confirmed (50 / 49 / 43). Committed as 'Add inspect_model.py'.
(The example row above is only an illustration. It is not in the Tasks sheet.)

## Progress
Week | Focus | Week starts | Tasks | Done | In progress | Blocked | % done | Hours logged | Planned hours
1 | Know your simulator | 46321 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
2 | Joint control | 46328 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
3 | Kinematics and reaching | 46335 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
4 | Take apart the walking policy | 46342 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
5 | Grasping the ball | 46349 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
6 | Reliable grasp and the first task chain | 46356 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
7 | The physics of the delivery | 46363 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
8 | Release, compare, report | 46370 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
Total |  |  | 48 | 0 | 0 | 0 | 0 | 0 | 108
Assumption
Planned h/week | 13.5 | Midpoint of the plan's 12–15 h per week budget.
Robotics tasks done | 0 of 40
ML tasks done | 0 of 8

## Tasks
ID | Week | Phase | Week focus | Day | Planned date | Track | Task | What to do | Done when | Status | Date done | Hours | Notes
W1-R1 | 1 | Phase 0 | Know your simulator | Mon | 46321 | Robotics | Build and run everything | Build the workspace and run every launch file in the README (RViz, MuJoCo hold, walking on both scenes). Write down every warning you see. | All four launch commands run and you can walk the robot to the table with the keyboard. | Not started
W1-R2 | 1 | Phase 0 | Know your simulator | Tue | 46322 | Robotics | Write scripts/inspect_model.py | Load bowling_scene.xml. Print nq/nv/nu, every body with its mass, the total robot mass, and each joint's name, qposadr, dofadr and range. | The printed sizes match the README (50 / 49 / 43) and you can say where any joint lives in qpos. | Not started
W1-R3 | 1 | Phase 0 | Know your simulator | Wed | 46323 | Robotics | Centre of mass and contacts | Let the free-base robot stand under JointHold for 5 s. Log subtree_com of the pelvis and foot contact forces with mj_contactForce. Plot both. | The sum of normal foot forces equals m·g within 2% once the robot settles. | Not started
W1-R4 | 1 | Phase 0 | Know your simulator | Thu | 46324 | Robotics | Timestep and integrator sweep | Run standing with timestep 0.001, 0.002, 0.005, 0.01 and integrators Euler, implicitfast, RK4. Record which combinations fall or blow up. | A table of 12 runs with the result (stable / falls / NaN) and the wall-clock time for each. | Not started
W1-R5 | 1 | Phase 0 | Know your simulator | Fri | 46325 | Robotics | Armature experiment | Set ankle-roll armature to 0, rerun standing, then restore it. Compute the ankle-roll natural frequency √(kp/I) with and without armature. | You can explain with numbers why the ankle went unstable at the old timestep. | Not started
W1-M1 | 1 | Phase 0 | Know your simulator | Week | 46327 | ML | PyTorch refresher | Tensors, autograd, nn.Module, an optimizer loop. Fit an MLP to y = sin(x) + noise with a train/validation split. | You can plot training and validation loss and explain overfitting from the plot. | Not started
W2-R1 | 2 | Phase 1 | Joint control | Mon | 46328 | Robotics | PD step response | Fixed base. Command a 0.5 rad step on the right shoulder pitch and elbow. Plot the response for kp ∈ {5, 20, 40, 100} with critical damping kd = 2√(kp·I). | Four plots, with rise time, overshoot and steady-state error written on each. | Not started
W2-R2 | 2 | Phase 1 | Joint control | Tue | 46329 | Robotics | Add gravity compensation | Add qfrc_bias as a feedforward torque. Repeat Monday's kp = 20 test. | Steady-state error drops by at least 5× compared with plain PD. | Not started
W2-R3 | 2 | Phase 1 | Joint control | Wed | 46330 | Robotics | Computed torque | Use mj_inverse to compute the torque for a desired acceleration, then add PD on the error. Track a 0.5 Hz sinusoid on the elbow. | An RMS-error table for PD, PD + gravity, and computed torque on the same trajectory. | Not started
W2-R4 | 2 | Phase 1 | Joint control | Thu | 46331 | Robotics | Smooth trajectories | Write a quintic polynomial between two arm poses (zero start/end velocity and acceleration). Track it with computed torque. | Joint velocity and acceleration plots are smooth, with no spikes at the start or end. | Not started
W2-R5 | 2 | Phase 1 | Joint control | Fri | 46332 | Robotics | Torque limits | Read actuator_ctrlrange for the arm. Speed the trajectory up until torques saturate and watch what tracking does. | You know the fastest arm swing the motors can follow. This number matters for bowling in week 7. | Not started
W2-M1 | 2 | Phase 1 | Joint control | Week | 46334 | ML | Learn forward kinematics | Sample 100k random right-arm poses, run mj_kinematics, record palm position. Train an MLP from joint angles to palm position. | Validation error under 1 cm, and you can explain why more data helped (or didn't). | Not started
W3-R1 | 3 | Phase 1 | Kinematics and reaching | Mon | 46335 | Robotics | Check the Jacobian | Compute the palm site Jacobian with mj_jacSite. Verify it against finite differences of the site position. | The two Jacobians agree to 1e-6. | Not started
W3-R2 | 3 | Phase 1 | Kinematics and reaching | Tue | 46336 | Robotics | Differential IK from scratch | Damped least squares: Δq = Jᵀ(JJᵀ + λ²I)⁻¹·e. Move the palm to tray_center with the base fixed. | The palm reaches within 1 cm of the tray from the zero pose. | Not started
W3-R3 | 3 | Phase 1 | Kinematics and reaching | Wed | 46337 | Robotics | Limits and posture | Clamp joint limits and add a null-space task that pulls the arm toward a comfortable posture. | No joint hits its limit, and the elbow stays below the shoulder. | Not started
W3-R4 | 3 | Phase 1 | Kinematics and reaching | Thu | 46338 | Robotics | Same task with mink | Rebuild the reach with mink (position plus palm-down orientation). Compare iterations and final error with your solver. | A short table comparing your IK with mink. | Not started
W3-R5 | 3 | Phase 1 | Kinematics and reaching | Fri | 46339 | Robotics | Robustness test | Run 20 random start poses through both solvers. Record success rate and iterations to converge. | At least 19 of 20 starts reach within 1 cm. | Not started
W3-M1 | 3 | Phase 1 | Kinematics and reaching | Week | 46341 | ML | Learned IK, and why it fails | Train an MLP from palm position to joint angles using week 2's data. Find poses with two IK solutions and look at what the network predicts. | You can show a case where the network averages two solutions into a wrong pose. This is why multimodal targets need other methods. | Not started
W4-R1 | 4 | Phase 2 | Take apart the walking policy | Mon | 46342 | Robotics | Label the observation | Write a table of all 47 observation entries in walk.py: index range, meaning, scale. | Every index from 0 to 46 is labelled and you can rebuild the vector by hand. | Not started
W4-R2 | 4 | Phase 2 | Take apart the walking policy | Tue | 46343 | Robotics | Headless evaluation script | Write scripts/eval_walk.py: N episodes of 15 s, a fall when pelvis height drops below 0.4 m, and lateral drift measured at the end. | One command prints fall rate and mean drift for a given speed. | Not started
W4-R3 | 4 | Phase 2 | Take apart the walking policy | Wed | 46344 | Robotics | Speed × hand-mass sweep | Sweep speed 0.3–1.0 m/s in 0.1 steps and hand_mass_scale ∈ {0.25, 0.5, 1.0}, with 50 episodes per cell. | A heatmap of fall rate. This is your baseline for retraining after month two. | Not started
W4-R4 | 4 | Phase 2 | Take apart the walking policy | Thu | 46345 | Robotics | Pushes and noise | Apply lateral pushes with xfrc_applied (20–100 N for 0.1 s) and add noise to the observation. | A curve of fall rate against push force. | Not started
W4-R5 | 4 | Phase 2 | Take apart the walking policy | Fri | 46346 | Robotics | Ablate your outer loops | Set heading_kp and speed_kp to 0 one at a time and rerun the 0.5 m/s case. | You can say in numbers how much each loop contributes. | Not started
W4-M1 | 4 | Phase 2 | Take apart the walking policy | Week | 46348 | ML | REINFORCE on CartPole | Implement the vanilla policy gradient from Spinning Up on Gymnasium CartPole-v1. Run 5 seeds. | A learning curve with mean ± std over 5 seeds that reaches 500 reward. | Not started
W5-R1 | 5 | Phase 3 | Grasping the ball | Mon | 46349 | Robotics | Know the hand | List the Dex3 joints, actuators and ranges. Write open and close commands for the right hand and test them in the air. | The fingers open and close smoothly with no jitter. | Not started
W5-R2 | 5 | Phase 3 | Grasping the ball | Tue | 46350 | Robotics | Pre-grasp and approach | Use your IK to place the palm 8 cm above the ball, then descend to the grasp pose. | The palm reaches the grasp pose without touching the tray. | Not started
W5-R3 | 5 | Phase 3 | Grasping the ball | Wed | 46351 | Robotics | Close, lift and tune contacts | Close the fingers, lift 15 cm, log fingertip contact forces. Tune ball friction, condim and solref if it slips. | The ball stays in the hand for a 3 s hold while the arm moves. | Not started
W5-R4 | 5 | Phase 3 | Grasping the ball | Thu | 46352 | Robotics | Failure log | Run 20 grasps and classify every failure: slip, knocked off, penetration, missed. | A failure table with a likely cause for each type. | Not started
W5-R5 | 5 | Phase 3 | Grasping the ball | Fri | 46353 | Robotics | Grasp state machine | Wrap it as states: PREGRASP → APPROACH → CLOSE → LIFT → HOLD, with a timeout and a success check in each state. | One function call runs the full grasp and reports success or the failing state. | Not started
W5-M1 | 5 | Phase 3 | Grasping the ball | Week | 46355 | ML | PPO from scratch | Implement PPO with GAE and the clipped objective (about 300 lines of PyTorch). Solve Pendulum-v1. | Average return above −200 on 3 seeds. | Not started
W6-R1 | 6 | Phase 3 | Reliable grasp and the first task chain | Mon | 46356 | Robotics | Randomize the ball | Shift the ball ±3 cm in x and y on each reset. Run 100 grasps. | A success rate measured on 100 trials. | Not started
W6-R2 | 6 | Phase 3 | Reliable grasp and the first task chain | Tue | 46357 | Robotics | Use the ball position | Read the ball pose from data and plan the pre-grasp from it instead of from tray_center. | Success rate above 90% on 100 randomized trials. | Not started
W6-R3 | 6 | Phase 3 | Reliable grasp and the first task chain | Wed | 46358 | Robotics | Stand while grasping | Free base. Walk to the table, command zero velocity, then grasp while the walking policy keeps balance. | The robot stays upright while the arm moves in 10 of 10 runs. | Not started
W6-R4 | 6 | Phase 3 | Reliable grasp and the first task chain | Thu | 46359 | Robotics | Task state machine | Write task.py: WALK_TO_TABLE → STOP → REACH → GRASP → LIFT → TURN, using your walk controller and grasp code. | The full chain runs in one command. | Not started
W6-R5 | 6 | Phase 3 | Reliable grasp and the first task chain | Fri | 46360 | Robotics | Measure the chain | Run the chain 20 times and record which stage fails. | A per-stage success table. Fix the worst stage first. | Not started
W6-M1 | 6 | Phase 3 | Reliable grasp and the first task chain | Week | 46362 | ML | Your PPO against SB3 | Run your PPO and Stable-Baselines3 PPO on Hopper-v4 with 3 seeds each. Then vary learning rate and clip range. | A comparison plot, and a list of which hyperparameters matter most. | Not started
W7-R1 | 7 | Phase 4 | The physics of the delivery | Mon | 46363 | Robotics | Projectile solver | From a release point 2.0 m high at the popping crease, solve for speed and angle that hit target. Include a bounce: real deliveries pitch before the stumps. | A function release_for(target, pitch_length) that returns speed and angle. | Not started
W7-R2 | 7 | Phase 4 | The physics of the delivery | Tue | 46364 | Robotics | Check it in simulation | Place the ball at the release point and set its qvel directly. Compare the simulated landing with your prediction. Add drag if needed. | Predicted and simulated landing points agree within 5 cm. | Not started
W7-R3 | 7 | Phase 4 | The physics of the delivery | Wed | 46365 | Robotics | Error budget | Perturb speed (±0.2 m/s), angle (±1°) and release time and record the miss distance at the stumps. | You know how precise the arm must be to hit stumps 22.9 cm wide. | Not started
W7-R4 | 7 | Phase 4 | The physics of the delivery | Thu | 46366 | Robotics | Parameterize the swing | Fixed base at the crease. Describe the bowling arm swing with 4–6 spline via-points. Keep the elbow near-straight: bowling allows at most 15° of elbow extension. | Forward simulation returns the hand velocity at release for any set of via-points. | Not started
W7-R5 | 7 | Phase 4 | The physics of the delivery | Fri | 46367 | Robotics | Optimize with CMA-ES | Optimize the via-points (pip cma) so the hand velocity at release matches Monday's solution, within torque limits from week 2. | The optimized swing gives a release velocity within 5% of the target. | Not started
W7-M1 | 7 | Phase 4 | The physics of the delivery | Week | 46369 | ML | Build a Gymnasium environment | Wrap the fixed-base throw as an env: observation (arm state, ball state), action (arm joint targets plus a release signal), reward (minus miss distance at the stumps). | gymnasium.utils.env_checker passes and a random policy runs for 100 episodes. | Not started
W8-R1 | 8 | Phase 4 + review | Release, compare, report | Mon | 46370 | Robotics | Release timing | Open the fingers at time t during the swing. Add ±10 ms jitter and measure the hit rate. | A plot of hit rate against release-time error. | Not started
W8-R2 | 8 | Phase 4 + review | Release, compare, report | Tue | 46371 | Robotics | Grasped ball, full swing | Start with the ball in the hand, run the optimized swing and release. 50 throws. | A measured hit rate on 50 throws with the ball released from the fingers. | Not started
W8-R3 | 8 | Phase 4 + review | Release, compare, report | Wed | 46372 | Robotics | Train PPO on the throw | Train PPO (yours or SB3) on the week 7 environment. Log returns and hit rate. | A learning curve, plus the number of simulated throws it took. | Not started
W8-R4 | 8 | Phase 4 + review | Release, compare, report | Thu | 46373 | Robotics | Optimizer versus RL | Compare CMA-ES and PPO on hit rate, simulated throws needed and robustness to ball-position noise. | A comparison table with a one-paragraph explanation of why the winner won. | Not started
W8-R5 | 8 | Phase 4 + review | Release, compare, report | Fri | 46374 | Robotics | Two-month report | Write docs/month2_report.md: what works, measured numbers, failure analysis, next steps (GPU retraining of walking, imitation of a bowling action). | The report links every result to a script that reproduces it. | Not started
W8-M1 | 8 | Phase 4 + review | Release, compare, report | Week | 46376 | ML | Plan month three | List what retraining walking with domain randomization needs: compute (your GTX 1650 has 4 GB), environment count, randomized parameters. | A one-page plan for Phase 6 with a rough compute estimate. | Not started

## Weeks
Week | Phase | Focus | Goal | Read this week | Deliverable (commit by Sunday) | Checkpoint questions (answer without notes)
1 | Phase 0 | Know your simulator | Read any MuJoCo model like an engineer: sizes, masses, contacts, and what makes a simulation stable. | • MuJoCo docs: Overview and Computation (Simulation pipeline, Contact) • MuJoCo Python tutorial notebook, first half | scripts/inspect_model.py, the contact-force plot, the sweep table, and notes/week1.md. | • Why does qpos have one more entry than qvel? • What does solref change in a contact, physically? • Why can a light link make PD control unstable at a fixed timestep?
2 | Phase 1 | Joint control | Make one arm follow a trajectory precisely with PD, gravity compensation and computed torque. | • Modern Robotics ch. 8.1–8.3 (dynamics) and ch. 11.1–11.4 (motion control) | scripts/arm_control.py with the three controllers and one comparison plot. | • What does qfrc_bias contain besides gravity? • Why does computed torque need an accurate model? • What happens to PD tracking when the torque saturates?
3 | Phase 1 | Kinematics and reaching | Move the right palm to the tray with your own differential IK, then with mink. | • Modern Robotics ch. 4–6 (forward kinematics, Jacobian, inverse kinematics) • Robotic Manipulation (Tedrake): Basic pick and place, differential IK | scripts/reach_tray.py, the 20-start table, and a short video of the reach. | • What does the damping λ trade off? • What is the null space of J and why is it useful on a 7-DoF arm? • Why does regression average over multiple solutions?
4 | Phase 2 | Take apart the walking policy | Treat motion.pt as a system under test: what it sees, where it breaks, and why. | • Rudin et al. 2021 (paper 5 in the reading guide) • Spinning Up: Intro to RL parts 1–3 | scripts/eval_walk.py, the heatmap, and a one-page evaluation report. | • Why is the gait phase part of the observation? • Why does the policy output joint targets rather than torques? • Why do you need 5 seeds before believing a learning curve?
5 | Phase 3 | Grasping the ball | Pick the ball from the tray with the Dex3 hand, base fixed, using a scripted controller. | • Robotic Manipulation (Tedrake): Grasping chapter (contact, friction cones, force closure) | g1_bowling_control/grasp.py, the contact-force plot, and a grasp video. | • What is a friction cone and how does condim change it? • Why does a grasp that works at rest fail when the arm accelerates? • What does GAE's λ trade off?
6 | Phase 3 | Reliable grasp and the first task chain | Grasp with the ball position randomized, then chain walking and grasping in one run. | • MuJoCo docs: XML reference for contact pairs and exclusions (as needed) • PPO paper (Schulman 2017), sections 3–5 | g1_bowling_control/task.py and the per-stage table. | • Why did feedback from the ball pose raise success so much? • How does arm motion disturb a walking policy that was trained with a rigid upper body? • Which PPO hyperparameter hurt most when wrong?
7 | Phase 4 | The physics of the delivery | Compute the release that hits the stumps, then find an arm swing that produces it. | • TossingBot (Zeng 2019), the throwing and residual-physics sections • MCC Laws of Cricket, Law 21.3 (fair delivery: the arm) | scripts/projectile.py, scripts/throw_opt.py, and the error-budget plot. | • Why is a throw with an extending elbow illegal in cricket, and how does it change your search space? • Which release error dominates the miss distance? • Why would a learned residual help on top of the physics model?
8 | Phase 4 + review | Release, compare, report | Bowl a real grasped ball from the hand, compare the optimizer with RL, and write up the two months. | • Domain randomization (Tobin 2017), to prepare for month three • Your own notes from weeks 1–7 | A demo video of a grasp-and-bowl, the comparison table, and docs/month2_report.md. | • Where did most of your hit-rate loss come from: grasp, swing or release? • When is a model-based optimizer better than RL? • What would change if the base were free and the robot had just run up?